## Data
RACI Chart Template
Project Name
Project Manager Name
Project Start Date |  |  | 2023-02-06
Task | Start Date | End Date | Status | Responsible | Accountable | Consulted | Informed
Task #1 | 2023-02-06 | 2023-03-31 | Done | Manager #1 | Employer #1 | Legal Department - Expert #1 | Stakeholder #1
Sub-task #1.1 | 2023-02-06 | 2023-03-20 | Done | Manager #1 | Employer #1
Sub-task #1.2 | 2023-03-20 | 2023-03-31 | Done | Manager #1 | Employer #1
Task #2 | 2023-04-01 | 2023-04-15 | In progress | Manager #2 | Employer #2 |  | Stakeholder #1
Task #3 | 2023-04-01 | 2023-04-15 | In progress | Manager #3 | Employer #3 | Financial Department - Expert #1 | Stakeholder #2
Task #4 | 2023-04-01 | 2023-04-30 | In progress | Manager #4 | Employer #4
Sub-task #4.1 | 2023-04-01 | 2023-04-15 | In progress | Manager #4 | Employer #4
Sub-task #4.2 | 2023-04-01 | 2023-04-07 | Delayed | Manager #4 | Employer #4
Sub-task #4.3 | 2023-04-07 | 2023-04-30 | Not started | Manager #4 | Employer #5
Sub-task #4.4 | 2023-04-15 | 2023-04-30 | Not started | Manager #4 | Employer #5
Task #5 | 2023-05-01 | 2023-05-15 | Not started
Task #6 | 2023-05-15 | 2023-05-31 | Not started
Task #7 | 2023-06-01 | 2023-06-30 | Not started
Task #8 | 2023-06-15 | 2023-07-15 | Not started
Task #9 | 2023-07-01 | 2023-07-15 | Not started
Task #10 | 2023-07-15 | 2023-10-01 | Not started

## Legend
Status
Not started
In progress
Delayed
Stopped
Done