## Example template
Project Plan Template
Project Name |  |  | ACS23
Project Manager |  |  | John Smith
Project Start Date |  |  | 2023-02-06
Project End Date |  |  | 2023-10-01
Duration (days) |  |  | 237
Task | Assigned to | Planed Start | Planned End | Planned Duration (days) | Real Start | Real End | Real Duration (days) | Status | Progress
Task #1 | Employer #1 | 2023-02-06 | 2023-03-31 | 53 | 2023-02-15 | 2023-04-15 | 59 | Done | 100%
Sub-task #1.1 | Employer #2 | 2023-02-06 | 2023-03-20 | 42 | 2023-02-15 | 2023-03-20 | 33 | Done | 100%
Sub-task #1.2 | Employer #3 | 2023-03-20 | 2023-03-31 | 11 | 2023-03-20 | 2023-04-15 | 26 | Done | 100%
Task #2 | Employer #4 | 2023-04-01 | 2023-04-15 | 14 | 2023-04-01 | 2023-04-15 | 14 | Done | 100%
Task #3 | Employer #5 | 2023-04-01 | 2023-04-15 | 14 | 2023-04-01 | 2023-04-15 | 14 | Stopped | 20%
Task #4 | Employer #6 | 2023-04-01 | 2023-04-30 | 29 | 2023-04-01 | 2023-04-30 | 29 | Done | 100%
Sub-task #4.1 | Employer #7 | 2023-04-01 | 2023-04-15 | 14 | 2023-04-01 | 2023-04-15 | 14 | Done | 100%
Sub-task #4.2 | Employer #8 | 2023-04-01 | 2023-04-07 | 6 | 2023-04-01 | 2023-04-07 | 6 | Done | 100%
Sub-task #4.3 | Employer #9 | 2023-04-07 | 2023-04-30 | 23 | 2023-04-07 | 2023-04-30 | 23 | Done | 100%
Sub-task #4.4 | Employer #10 | 2023-04-15 | 2023-04-30 | 15 | 2023-04-15 | 2023-04-30 | 15 | Done | 100%
Task #5 | Employer #11 | 2023-05-01 | 2023-05-15 | 14 | 2023-05-01 | 2023-05-15 | 14 | Done | 100%
Task #6 | Employer #12 | 2023-05-15 | 2023-05-31 | 16 | 2023-05-15 | 2023-05-31 | 16 | Done | 100%
Task #7 | Employer #13 | 2023-06-01 | 2023-06-30 | 29 | 2023-06-01 | 2023-06-30 | 29 | In progress | 5%
Task #8 | Employer #14 | 2023-06-15 | 2023-07-15 | 30 | 2023-06-15 | 2023-07-15 | 30 | Delayed | 0%
Task #9 | Employer #15 | 2023-07-01 | 2023-07-15 | 14 | 2023-07-01 | 2023-07-15 | 14 | Not started | 0%
Leave | Employer #16 | 2023-07-15 | 2023-08-15 | 31 | 2023-07-15 | 2023-08-15 | 31 | Not started | 0%
Task #10 | Employer #17 | 2023-08-15 | 2023-10-01 | 47 | 2023-08-15 | 2023-10-01 | 47 | Not started | 0%
Formulas:
Planed Start = MIN([Planed Start, row below]:C12)
Planned End = MAX([Planned End, row below]:D12)
Real Start = MIN([Real Start, row below]:F12)
Real End = MAX([Real End, row below]:G12)

## Blank template
Project Plan Template
Project Name
Project Manager
Project Start Date
Project End Date
Duration (days)
Task | Assigned to | Planed Start | Planned End | Planned Duration (days) | Real Start | Real End | Real Duration (days) | Status | Progress
Task #1 |  | 2023-07-01 | 2023-07-01 | 0 | 2023-07-01 | 2023-07-01 | 0 | Not started | 0%
Subtask #1 |  | 2023-07-01 | 2023-07-01 | 0 | 2023-07-01 | 2023-07-01 | 0 | Not started | 0%
Subtask #2 |  | 2023-07-01 | 2023-07-01 | 0 | 2023-07-01 | 2023-07-01 | 0 | Not started | 0%
Subtask #3 |  | 2023-07-01 | 2023-07-01 | 0 | 2023-07-01 | 2023-07-01 | 0 | Not started | 0%
Subtask #4 |  | 2023-07-01 | 2023-07-01 | 0 | 2023-07-01 | 2023-07-01 | 0 | Not started | 0%
Subtask #5 |  | 2023-07-01 | 2023-07-01 | 0 | 2023-07-01 | 2023-07-01 | 0 | Not started | 0%
Subtask #6 |  | 2023-07-01 | 2023-07-01 | 0 | 2023-07-01 | 2023-07-01 | 0 | Not started | 0%
Subtask #7 |  | 2023-07-01 | 2023-07-01 | 0 | 2023-07-01 | 2023-07-01 | 0 | Not started | 0%
Subtask #8 |  | 2023-07-01 | 2023-07-01 | 0 | 2023-07-01 | 2023-07-01 | 0 | Not started | 0%
Formulas:
Planed Start = MIN([Planed Start, row below]:C12)
Planned End = MAX([Planned End, row below]:D12)
Real Start = MIN([Real Start, row below]:F12)
Real End = MAX([Real End, row below]:G12)

## Legend
Status
Not started
In progress
Delayed
Stopped
Done