## Task list
Project Task List Template
Project Name
Project Manager Name
Project Start Date |  |  | 2023-02-06
Estimated Project End Date |  |  | 2024-02-28
Task | Assigned to | Start Date | End Date | Task Duration (days) | Task duration (hours) | Current hours | Budget | Current expense | Status | Progress
Task #1 | Employer #1 | 2023-02-06 | 2023-03-31 | 53 | 424 | 420 | 500 | 450 | Done | 100%
Sub-task #1.1 | Employer #2 | 2023-02-06 | 2023-03-20 | 42 | 336 | 336 | 200 | 200 | Done | 100%
Sub-task #1.2 | Employer #3 | 2023-03-20 | 2023-03-31 | 11 | 88 | 84 | 300 | 250 | Done | 100%
Task #2 | Employer #4 | 2023-04-01 | 2023-09-15 | 167 | 1336 | 700 | 2000 | 800 | In progress | 50%
Task #3 | Employer #5 | 2023-04-01 | 2023-08-15 | 136 | 1088 | 220 | 1000 | 200 | In progress | 20%
Task #4 | Employer #6 | 2023-04-01 | 2023-07-30 | 120 | 960 | 320 | 1000 | 500 | In progress | 30%
[5 empty] | 0 |  |  |  | Not started | 0%
[5 empty] | 0 |  |  |  | Not started | 0%
[5 empty] | 0 |  |  |  | Not started | 0%
[5 empty] | 0 |  |  |  | Not started | 0%
[5 empty] | 0 |  |  |  | Not started | 0%
[5 empty] | 0 |  |  |  | Not started | 0%
[5 empty] | 0 |  |  |  | Not started | 0%
[5 empty] | 0 |  |  |  | Not started | 0%
[5 empty] | 0 |  |  |  | Not started | 0%
[5 empty] | 0 |  |  |  | Not started | 0%
[5 empty] | 0 |  |  |  | Not started | 0%

## Legend
Status
Not started
In progress
Delayed
Stopped
Done